## 10 Day Plan
PropAnalytics — 10-Day Demo Plan ¦ All 4 Members ¦ Apr 7–17
Jackson · Joey · Jack · Gurgot — NO git commits from Replit agent
# | Task | Owner | Branch | Due | Depends On | Notes
DAY 1 — Unblock everything
1 | nba_api game log ingestion — fetch_and_store_gamelogs(), match players by name, write last 15 games to GameLog table | Jackson | feat/gamelog-ingestion | Day 1 | — | THE blocker. Everything with hit rates returns zero until this runs. nba_api is installed, never called.
2 | POST /api/admin/fetch-gamelogs route — triggers ingestion, returns JSON summary of players updated | Jackson | feat/gamelog-ingestion | Day 1 | #1 | Same branch as #1. Gives the team a way to manually refresh logs during dev.
3 | screener.js — real inputs (Prop Type, Odds, Hit%, Sample Size), fetch() /api/screener/props, render result cards | Jackson | feat/screener-wired | Day 1 | — | API already works. Build the JS now, real data flows in automatically once #1 lands.
4 | search.js — fetch() /api/odds/games, replace 3 placeholder game cards with real home/away/time data | Jackson | feat/games-wired | Day 1 | — | /api/odds/games is live and returns real data right now. 20 lines of JS.
DAYS 1–2 — Homepage comes alive
5 | Enrich Player records — populate team + position from nba_api after ingestion (currently name-only) | Gurgot | feat/player-enrich | Day 2 | #1 | fetch_and_store_props() only saves player name. Need team + position for display on game/player pages.
6 | Fix GET /api/player/<name> — replace hardcoded zero response with real nba_api season averages | Gurgot | feat/player-real-data | Day 2 | #1 #5 | Route exists, returns {points_per_game: 0} hardcoded. TODO comment is already in the file.
DAYS 2–3 — New routes + player data fix
7 | GET /api/player/<id>/gamelogs — return last 15 GameLog rows for a player as JSON | Gurgot | feat/player-log-route | Day 3 | #1 | Simple DB query — GameLog by player_id order by date desc limit 15. Feeds Joey's game log table.
8 | GET /api/player/<id>/props — return all current PlayerProp rows for a player with hit_rate attached | Gurgot | feat/player-props-route | Day 3 | #1 #6 | Query PlayerProp by player_id, call hit_rate() for each row. Feeds Joey's prop summary cards.
9 | game.py — GET /game/<event_id> renders game.html, GET /api/game/<event_id>/props returns props + hit rates for that game | Jack | feat/game-routes | Day 3 | #1 | game.py is an empty file. Filter PlayerProp by Game.odds_event_id. Include hit_rate per prop row.
DAYS 3–5 — Game page
10 | game.html — matchup header (home vs away, tip-off time), props table (player, stat, line, hit%, odds), click row → player page | Jack | feat/game-page | Day 4 | #9 | game.html is empty. Fetch /api/game/<event_id>/props on load. Sortable by hit rate column.
11 | game.html — Chart.js bar chart: hit rate per prop for this game, dashed line at 50% | Jack | feat/game-chart | Day 5 | #10 | Makes the page look real for demo. Each prop on Y axis, hit% bar on X. Import Chart.js via CDN.
DAYS 4–6 — Player detail page
12 | player.html — header (name, team, position, avg stats), prop summary cards (hit rate, streak, over/under split) | Joey | feat/player-page | Day 5 | #6 #8 | Joey is already on this. Fetch /api/player/<id> for header. Fetch /api/player/<id>/props for cards.
13 | player.html — game log table: last 15 games (date, opp, pts, reb, ast, min), rows highlight vs prop line | Joey | feat/player-page | Day 6 | #7 #12 | Same branch. Fetch /api/player/<id>/gamelogs. Green row if over line, red if under.
14 | player.html — Chart.js line chart: stat over last 15 games, dashed horizontal = current prop line | Joey | feat/player-chart | Day 7 | #13 | One chart per stat type (pts/reb/ast). Most impressive thing on the page for demo.
DAYS 6–8 — Wire all pages together
15 | base.html — shared nav/header/footer template, all pages extend it, gambling disclaimer in footer | Jackson | feat/base-template | Day 7 | #10 #12 | base.html is empty. DRY up shared CSS and nav. Disclaimer is a non-functional req from project spec.
16 | Navigation — homepage game card → game.html, game prop row → player.html, screener card → player.html | Jackson | feat/nav-wiring | Day 8 | #4 #10 #12 | Pass event_id and player_id as URL params. Every page must be reachable by clicking, not typing URLs.
17 | home.py — move homepage render here from player.py, add /api/games/today route pulling today's games from DB | Gurgot | feat/home-routes | Day 7 | #9 | home.py is empty, homepage render is misplaced in player.py. Minor cleanup but fixes routing logic.
DAYS 8–10 — Polish + demo prep
18 | Loading spinners on all fetch() calls, empty state messages, last-updated timestamps in section headers | Jackson | feat/polish | Day 9 | #3 #4 #10 #12 | Non-functional req: low latency feel. Spinner while fetching, 'No results' if empty, timestamp in header.
19 | Attach fetch-gamelogs to fetch_and_store_props() — auto-refresh logs whenever props are fetched | Gurgot | feat/gamelog-auto-sync | Day 8 | #1 #2 | So DB stays fresh without manual admin trigger. One function call added to existing pipeline.
20 | Full demo dry run — every click, every page, fix anything broken or blank | All | feat/demo-dryrun | Day 10 | All | Full flow: screener → player. Homepage → game page → player page. Nothing should crash or show placeholder.